## Sheet1
Summary | Status | Effort Level
ARA-38 Implement Context Slicing with Nearest Line Break Logic and Source Header Preservation | In Discussion | Medium
ARA-37 Prevent Overlapping Context When Rehydrating Consecutive Chunks | In Discussion | Low
ARA-36 Analyze LLM Responses for Chapter 3a Multi-Level Chunking with Token & Cost Metrics | In Discussion | Medium
ARA-35 Reset and Standardize Environments Across GitHub Branches | In Discussion | Medium
ARA-34 American Retirement Association: Analysis & Requirement Gathering | In Discussion | High
ARA-24 Verify Uploaded Chapters on Demo Website for Completeness and Accuracy | In Active Development | Medium
ARA-23 Upload All Chapters to Demo Website via Admin Portal | Completed / Handed Off | Medium
ARA-22 Query Construction – Phase 1: Logging, Review & Validation | In Active Development | Medium
ARA-21 Query Construction – Phase 1: Unclear Concept Detection (Design & Implementation) | Completed / Handed Off | Low
ARA-20 Query Construction – Analysis & Scope Validation | Completed / Handed Off | Low
ARA-19 ARA Environment Setup for 3-Level vs Multi-Level Chunking Verification | Completed / Handed Off | Medium
ARA-18 Validate 3-Level vs Multi-Level Chunking for Chapter 3A | Completed / Handed Off | Medium
ARA-17 UI Updates – ARA Admin Panel | Completed / Handed Off | Medium
ARA-16 UI Updates – ARA Response Page | Completed / Handed Off | Low
ARA-15 UI Updates – ARA Landing Page | Completed / Handed Off | Medium
ARA-14 Investigate Page Load Slowness Related to VPN Usage | Completed / Handed Off | Medium
ARA-13 Optimize Database Reads and Introduce Caching | Completed / Handed Off | Medium
ARA-12 Move Frontend Firebase Calls to Backend API | Completed / Handed Off | Low
ARA-11 Document Chunking Validation and Retrieval Testing | Completed / Handed Off | High
ARA-10 Chunking and Structuring Chapters for ARA Document Ingestion | Completed / Handed Off | High
ARA-9 POC: Implement Hierarchical Fallback-Based Rehydration Strategy for Chunk Matching | Completed / Handed Off | Medium
ARA-8 POC: Chapter-wise Chunk Upload via Admin Console | Completed / Handed Off | Medium
ARA-7 POC: Verify ARA Responses After Final Documents Upload | Completed / Handed Off | High
ARA-6 POC: Refine Chunk Matching & Controlled Rehydration to Prevent Context Overflow | Completed / Handed Off | Medium
ARA-5 POC: Implement Neighboring Section Rehydration Logic for Precise Context Control | Completed / Handed Off | Medium
ARA-4 POC: Define and Implement Firestore Document Chunk Storage for Controlled Context Injection | Completed / Handed Off | High
ARA-3 POC: Response Rehydration Not Following Required Manual 4-Step RAG Flow (Using Response API) | Completed / Handed Off | High
ARA-2 POC: Clone Existing DevPixel Website for ARA | Completed / Handed Off | High
ARA-1 POC: Infrastructure Outline | Completed / Handed Off | Low